## Sheet1
Description of risks and their final status
Risk | Probability | Financial Impact | Operational Impact | Stakeholder Concern | Overall Consequence | Final Risk Status
R01 (Demolition subcontractor unavailability) | High | Project delay (cost implication > £600k/monthly) | Major operational disruption | High concern from Project Director/Stakeholders | High | Resolved
T19 (Recycling objection risk) | High | £200k cost increase | Minor operational impact | Moderate concern (limited to environmental groups) | Medium | Happened
T16 (Concrete supply delay) | Moderate | Up to £400k cost increase and 1 month delay | Major operational disruption | High concern from stakeholders | High | Resolved